## retrospective_week
What went well | What to improve | What actions are being taken
AI DB groundwork set: PostgreSQL + Prisma + pgVector direction confirmed | Decide storage: OneDrive vs AWS S3 with cost/feature comparison | Remove event sourcing from docs (done) and update technical architecture
Removed event-sourcing pattern to simplify architecture | Finalize chunking strategy and evaluation metrics | Set up pgVector in codebase and document setup
Document->Parse/chunk embeddings. Agreed on pipeline. | Tighten meeting structure and timeboxing | Run head to head LLM tests on a 50 page sample; log results in spreadsheet
LLM shortlist & test plan defined (GPT, Grok, Gemini, Claude) | Consolidate feature definitions to avoid disjoint expectations | Create cost tracker & token limits in API layer
Early cost controls discussed (token limits, smaller test docs) | Add privacy/compliance plan for file + embeddings storage | Deliver Figma v1.2 with dashboard + revisions
UX direction clarified: single dashboard, sidebar nav, integrated uploads | Define collaboration model for study spaces (permissions, activity log) | Produce OneDrive vs S3 comparison doc
Beta tester outreach kicked off | Plan realistic simulation load tests (100-500 users) and success metrics | Prepare paper prototypes; Collect user feedback from detailed interviews
Interim report structure drafted; sections assigned | Integrate learning-theory rationale into design write ups | Draft database schema & migrations for study spaces and documents